## Sheet1
Decision ID | Date | Decision Summary | Impact Area | Decision Maker | Alternatives Considered | Final Decision | Rationale | Follow-up Actions
D001 | 2025-01-08 | Proceed with full automation of onboarding workflow | Service Desk Operations | ITSM Steering Committee | Manual onboarding, phased automation | Approved | Automation reduces provisioning time and human error | Update workflow design, test in sandbox, schedule training
D002 | 2025-01-15 | Defer CMDB Auto-Discovery until post-launch | Asset Management | Project Sponsor | Enable auto-discovery at go-live, manual import only | Deferred | Need more testing and integration validation | Create post-launch task, document known limitations
D003 | 2025-01-22 | Use standard change template for software updates | Change Management | CAB | Custom change form, no change control | Approved | Improves consistency and aligns with compliance standards | Publish template, train agents on usage