## README
Field | Description
Type (Risk/Assumption/Issue/Dependency) | Classify the entry as a Risk, Assumption, Issue, or Dependency.
ID | Unique identifier for tracking (e.g., R001, I002).
Description | Detailed explanation of the risk, assumption, issue, or dependency.
Impact | Impact level on the project (Low/Medium/High).
Likelihood (for Risks) | Estimate the likelihood for risks only (Low/Medium/High).
Owner | Person accountable for managing or resolving the entry.
Date Identified | Date the entry was first identified or raised.
Target Resolution Date | Target date by which the entry should be addressed or resolved.
Status | Current status (Open, In Progress, Resolved, Closed, etc.).
Resolution/Action Taken | Actions taken to address or resolve the entry.
Notes | Additional context or updates for tracking history.

## RAID Log
Type (Risk/Assumption/Issue/Dependency) | ID | Description | Impact | Likelihood (for Risks) | Owner | Date Identified | Target Resolution Date | Status | Resolution/Action Taken | Notes
Risk | R001 | Third-party integration may delay go-live due to API instability. | High | High | IT Project Lead | 2024-08-01 | 2024-09-15 | Open |  | Monitor API performance weekly.
Assumption | A001 | Service desk agents will be trained before go-live. | Medium |  | Training Manager | 2024-08-05 | 2024-09-10 | Open |  | Coordinate with HR for training sessions.
Issue | I001 | Asset import from legacy system failed partial records. | High |  | Asset Team Lead | 2024-08-10 | 2024-08-20 | In Progress | Re-import after cleansing data. | Escalated to vendor support.
Dependency | D001 | User provisioning requires Azure AD sync setup by IT. | High |  | Infrastructure Manager | 2024-08-03 | 2024-08-25 | Pending |  | Blocked until security review is complete.