## Master Checklist
Task Name | Owner | Target Date | Status | Notes
Verify All Workflows Are Active and Published | Implementation Admin | 2025-07-12 | In Progress | Ensure no draft workflows left
Validate Agent Roles and Group Assignments | System Admin | 2025-07-11 | Complete | Confirm with security lead
Test Email Routing and Notifications | Messaging Admin | 2025-07-10 | Complete | Include reply detection
Complete Agent Training Sessions | Training Coordinator | 2025-07-09 | Complete | Session recording uploaded
Review SLA and Escalation Policies | Process Owner | 2025-07-11 | In Progress | Escalation logic still under test
Confirm Request Portal Branding and Usability | UX Lead | 2025-07-12 | In Progress | Feedback from pilot pending
Test Service Catalog Forms and Approvals | Service Owner | 2025-07-12 | In Progress | Sample requests being submitted
Verify Asset Import and CMDB Health | Asset Manager | 2025-07-10 | Complete | Discovery Probe validated
Ensure Knowledge Base Articles Are Published and Linked | Knowledge Manager | 2025-07-10 | Complete | Top articles reviewed
Schedule Go-Live Communications Blast | Change Manager | 2025-07-11 | Not Started | Template pending approval

## Risk & Rollback Tracker
Risk/Issue | Impact | Severity | Contingency Plan | Owner
Workflow Errors Post-Go-Live | Workflows may not trigger correctly | Medium | Revert to manual triage | Workflow Owner
Email Notification Failure | Users may not receive ticket alerts | High | Notify via Teams and escalate to vendor | Messaging Admin
Knowledge Base Incompleteness | Users may not find answers, increasing ticket volume | Medium | Add placeholder article links | Knowledge Lead

## Go-Live Comms Plan
Communication Activity | Content Summary | Due Date | Owner
Announcement Email to All Staff | What is Freshservice, how to access it | 2025-07-11 | Comms Team
Slack Message with Portal Link | Quick tips and service catalog highlights | 2025-07-11 | IT Operations
Manager Briefing Deck | What team leads should know | 2025-07-10 | Project Manager

## Hypercare Prep
Preparation Task | Purpose | Target Date | Owner
Create Hypercare Support Queue | Route go-live issues separately for fast triage | 2025-07-12 | Admin Team
Publish Post-Go-Live FAQ | Cover common questions about workflows and access | 2025-07-12 | Knowledge Team
Assign Daily Hypercare Standup Facilitator | Lead check-ins and resolve roadblocks | 2025-07-11 | Hypercare Lead