## Sheet1
Step | Responsible Role | Status
1. Define Stakeholders | Change Manager | Not Started
2. Document Existing Change Processes | Process Owner | Not Started
3. Identify Change Types | IT Ops | Not Started
4. Gather Historical Incident Data Related to Changes | Service Desk Lead | Not Started
5. Define Fields for Change Forms | Change Manager | Not Started
6. Draft Change Templates (e.g., Firewall Change, Software Upgrade) | Change Manager | Not Started
7. Define Approval Routing Logic | ITSM Admin | Not Started
8. Schedule and Structure CAB Meetings | CAB Coordinator | Not Started
9. Determine Change Type Classification Rules | Change Manager | Not Started
10. Map Workflows in Workflow Automator | ITSM Admin | Not Started
11. Link Change Tickets to Other Modules (Incidents, Problems, Releases, Assets) | ITSM Admin | Not Started
12. Define SLA and Reminder Rules | ITSM Admin | Not Started
13. Enable Reporting and Dashboards | Reporting Analyst | Not Started
14. Plan Post-Implementation Review Process | Change Manager | Not Started
15. Establish Metrics for Success (approval rate, change success rate, etc.) | CAB | Not Started
16. Review with Stakeholders and Iterate | All Stakeholders | Not Started