## Onboarding-Offboarding Native
Step | Description | Owner | Dependencies | Completed (Y/N) | Notes
1 | Add Stakeholders - Define roles like HR Coordinator, IT Provisioner, Security Lead, Hiring Manager | Admin | None
2 | Configure Onboarding Settings - Go to Admin > Global Settings > Employee Onboarding | Admin | Step 1
3 | Build Kits - Create catalog items and use them in kit builder | Admin | Step 2
4 | Create Tickets - Use default Master + child ticket templates | Admin | Step 3
5 | Modify Approvals - Link to Reporting Manager and setup auto-approvals | Admin | Step 4
6 | Integrate Orchestration - Use App Node for provisioning/deprovisioning (Azure AD, Okta, etc.) | IT | Step 5
7 | Test Complete Workflow - Validate end-to-end functionality | QA | Steps 1-6
8 | Document Workflow - Save logic as JSON exports or screenshots | Admin | Step 7
9 | Review and Audit Quarterly - Update tasks and kits | Admin/HR | Step 8