## Portal Branding Checklist
Section | Item | Description | Completed (Y/N) | Notes
Branding | Logo Upload | Upload company logo to the portal | Y | Used white logo variant
Branding | Theme Colors | Apply brand-compliant color scheme | Y | Primary hex: #004080
Branding | Fonts & Typography | Match portal fonts with internal guidelines | N | Pending approval from design team
Branding | Portal Name | Set custom name for the portal | Y | Named: TechHelp
Branding | Custom URL | Configure custom support URL | N | Blocked by domain team

## Homepage Content Plan
Element | Content Type | Purpose | Status | Examples / Notes
Welcome Message | Text | Greet users and direct them to key functions | Completed | Welcome to TechHelp! Start by searching for help or submitting a request.
Quick Links | Buttons/Icons | Speed access to top requests | Planned | Reset Password, Request Laptop, Book Meeting Room
Announcements | Banner | Highlight seasonal or critical updates | Live | System Maintenance - July 8, 9pm EST
KB Highlights | Widget | Promote top-viewed and new articles | In Progress | Top 5 Articles / Recently Added / Most Helpful
Department Views | Role Filter | Segment experience by user group | Not Started | IT, HR, Facilities

## Portal Launch Tasks
Phase | Task | Owner | Due Date | Status | Dependencies/Notes
Pre-Launch | Finalize layout and icons | UI Team | 2025-07-10 | In Progress
Pre-Launch | Content Review (HR/IT) | Content Leads | 2025-07-12 | Planned | Review service descriptions
Launch | Send portal announcement email | Comms | 2025-07-15 | Not Started | Coordinate with branding
Launch | Publish portal and validate links | Admin | 2025-07-15 | Not Started
Post-Launch | Monitor user engagement analytics | Analytics Team | 2025-07-22 | Planned | Use Freddy Insights

## Portal Feedback Tracker
Date | User Group | Feedback | Category | Action Taken | Status
2025-07-17 | HR | Can't find onboarding forms | Navigation | Added onboarding link to Quick Links | Resolved
2025-07-18 | Finance | Font too small on mobile | Accessibility | Escalated to design team | Open
2025-07-19 | IT | Useful articles, but not easy to search | Search | Improved tagging and keywords | In Progress

## Usage Metrics
Metric | Value | Observation | Last Updated
Portal Visits | 1,245 | Up 15% since branding update | 2025-07-19
Tickets Submitted via Portal | 980 | Preferred over email | 2025-07-19
Article Views | 2,305 | New articles are trending | 2025-07-19
Top Clicked Service | Reset Password | Consistently top-used | 2025-07-19
Abandoned Searches | 120 | Improve keywords or article mapping | 2025-07-19