## Hypercare Setup Checklist
Step | Owner | Status
Create Hypercare queue in Freshservice | Admin | Pending
Assign agents to Hypercare group | Team Lead | Pending
Set SLA priority rules | Admin | Pending
Enable Freddy Copilot for AI suggestions | Admin | Pending
Define escalation path for critical issues | Ops Manager | Pending

## Hypercare Issue Tracker
Issue ID | Description | Reported By | Priority | Status | Assigned To
101 | Users can't find Reset Password form | HR | High | Open | Dev
102 | Notifications missing for new tickets | IT | Medium | Open | Admin

## Feedback Survey Questions
Question
What was easy to use in the new portal?
What didn’t work as expected?
Was the KB article helpful for your request?
How likely are you to recommend Freshservice to a colleague? (1-10)

## UAT Issue Carry-Forward Log
Issue ID | Issue Description | Raised By | Priority | Status | Assigned To | Date Identified | Resolution Date | Notes
UAT-001 | Approval workflow not triggering | IT | High | Open |  | 2025-07-01

## Daily Hypercare Standup Agenda
Date | Facilitator | Outstanding Issues | New Issues | Agent Feedback | Blockers | Action Items
2025-07-07 | Jane Doe | 3 | 2 | More KB usage guidance needed | None | Update KB article

## Post-Hypercare Summary Report
Metric | Value | Notes
Total Tickets Logged | 158
Tickets Resolved | 150
Top Issue Category | Access Requests
Average First Response Time | 1.5 hours
CSAT Score | 92% | Based on 74 responses
Lessons Learned |  | Need clearer onboarding guide
Next Steps |  | Schedule post-hypercare review meeting