## PIR Checklist
Step | Owner | Due Date | Status
Validate Freshservice system performance post-go-live
Collect key metrics (SLA, CSAT, ticket volume)
Confirm final documentation is complete and delivered
Host post-implementation review meeting
Transfer ownership to internal ops or MSP
Share training resources and admin console access
Create 30–90–180 day optimization roadmap
Schedule 60-day check-in with stakeholders

## Optimization Roadmap
Phase | Suggested Improvements | Owner | Status
Day 30 | Review user feedback and address quick wins
Day 90 | Automate repetitive ticket flows and approval steps
Day 180 | Integrate Freshservice with HRMS or ERP, expand asset tracking

## PIR Meeting Agenda
Time | Topic | Owner | Notes
10:00 AM | Welcome and Introductions | Project Manager
10:10 AM | Review of Project Objectives | Project Sponsor
10:20 AM | Key Metrics and Outcomes | Analytics Lead
10:40 AM | Open Issues and Lessons Learned | All Stakeholders
11:00 AM | Future Optimization Opportunities | Implementation Lead
11:20 AM | Handoff and Support Plan | Operations Manager
11:40 AM | Q&A and Final Feedback | Facilitator
12:00 PM | Adjourn

## Documentation Handoff
Document Name | Description | Format | Owner | Location
Configuration Workbook | Details on fields, automations, and service catalog | Excel | Admin Team | SharePoint > Freshservice
Role-Permission Matrix | Defines access levels for each role | Excel | Security Team | SharePoint > Freshservice
Training Materials | Guides, videos, and cheat sheets used for training | PDF/Video | Training Team | LMS / Knowledge Base
Hypercare Summary Report | Issues resolved and feedback collected during hypercare | Word | Project Team | Project Folder
Knowledge Base Article List | List of all published KB articles | Excel | Knowledge Manager | Freshservice KB Export

## Handoff to Operations
Responsibility | Assigned To | Notes | Date of Transfer
User Management | IT Admin | Includes onboarding and deactivation
Automation Updates | Automation Owner | Workflow automator and scenario automations
SLA Policy Changes | Service Owner | Changes to response/resolution targets
Knowledge Base Maintenance | Knowledge Manager | Article review and publishing
Freshservice Support Contact | Support Lead | Named contact for vendor escalation
Quarterly Review Planning | Process Owner | Schedule next review cycle for improvements